## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations required for doing project
|  | 2 | LLM for Contract analysis
|  | 3 | Clause Identification and Risk Analysis Engine
|  | 4 | Update tracking and Contract Modification
Note on F1: ====== ID#AAABv6zxcdw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day12 | Day 13 | Day 14
1 |  | Foundations required for doing project | Nov 10th | Nov 24th | Tammina Varaha Venkata Prasad | Learnt about fundamentals required for the project | Done | Introduction Session | Python and Jupyter Installation done | Learnt about Keywords and naming conventions | Learned about variables and Agile sheet filling | Multi Variables and Datatypes | Revised and practiced previous topics | Revised all the concepts covered | learnt about range(),mutable& immutable,control statements | learnt about loops and types of functions | learnt about functions with return keyword,arguments and types | learnt about modules and keywords | learnt about oops concepts | Constructors and instance variables | Revised constructors and Functions
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Tammina Varaha Venkata Prasad | Understood about the project,LLM and Executed demo codes | Done | Project overview | Presentation about Project | Creation of Virtual Environment | introduction to Tech Tools required for this project | Project Presentation Session | Practised Python Concepts | Revised previous concepts | overview about prompt engineering | AI, Data Science, GEN AI,fundamentals of LLM | Learned about LLM and Groq API key | Hands on implementation of Demo code | Packages and workflow milestone 2 | Revised Prompt Engineering | Practiced Demo codes
3 |  | Caluse Detection & Risk Analysis Engine | Dec 10th | Dec 24th | Tammina Varaha Venkata Prasad | Understood about LLM and execution of the project | Done | Overview about workflow and Project Structure | Understanding about Extraction of clauses from pdf | Learnt about text extraction and overlapping | Understanding about Cleaning the clauses and chunking | Understanding about clause identification and extraction | Revised extraction and chunking topics | Revised this week topics | Discussed about the assignment | Discussion on risk engine analysis and hands on implementation | discussion on run and pipeline Codes and Intro for Regulatory Update Tracking | Practised milestone1 and milestone 2 | Regulatory Update Tracking | Worked on Assignment task 1 | Worked on Assignment task 2
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Tammina Varaha Venkata Prasad | Understood Regulatory Update Tracking System &Contract Modification | Done | Working of Assignment | Discussed about assignment presentation | Learnt about Regulatory Update Tarcking System | Regulatory update Tracking System and Assignment presentation | Executed demo 2 & 3 codes and understood building the regulatory update tracking | Revised Previous session topics | Practiced milestone-3 demo codes | Contract Modification and Ammendment Engine | Revised Milestone3 topics | Implementation of milestone 3 code | Practised Milestone 3 demo codes | FeedParser and Milestone 3 execution | Slack Integration | Implementated Slack Integration

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7